## Dashboard
Design Risk Summary | [8 empty] | Civil |  | Civil |  | Design Co-ordination Notes
Designer | Pre-Mitigation Risk |  |  |  | Post Mitigation Risk |  |  |  | Pre-Mitigation Risk | 10 | Post Mitigation Risk | 7
| H | M | L | Total | H | M | L | Total |  |  |  |  | 1
Civil | 1 | 2 | 3 | 6 | 0 | 1 | 5 | 6
% | 16.67% | 33.33% | 50% | 100% | 0% | 16.67% | 83.33% | 100% |  |  |  |  | 2
Electrical | 1 | 2 | 3 | 6 | 0 | 1 | 5 | 6
% | 16.67% | 33.33% | 50% | 100% | 0% | 16.67% | 83.33% | 100% |  |  |  |  | 3
WTG | 3 | 2 | 1 | 6 | 0 | 1 | 5 | 6
% | 50% | 33.33% | 16.67% | 100% | 0% | 16.67% | 83.33% | 100% |  |  |  |  | 4
Other 1 | 1 | 2 | 3 | 6 | 2 | 1 | 3 | 6
% | 16.67% | 33.33% | 50% | 100% | 33.33% | 16.67% | 50% | 100% |  |  |  |  | 5
Other 2 | 1 | 2 | 3 | 6 | 1 | 2 | 3 | 6
% | 16.67% | 33.33% | 50% | 100% | 16.67% | 33.33% | 50% | 100% | Electrical |  | Electrical |  | 6
Other 3 | 3 | 2 | 1 | 6 | 0 | 1 | 5 | 6 | Pre-Mitigation Risk | 10 | Post Mitigation Risk | 7
% | 50% | 33.33% | 16.67% | 100% | 0% | 16.67% | 83.33% | 100% |  |  |  |  | 7
Total | 10 | 12 | 14 | 36 | 3 | 7 | 26 | 36
% | 27.78% | 33.33% | 38.89% | 100% | 8.333% | 19.44% | 72.22% | 100% |  |  |  |  | 8
Total | [12 empty] | 9
| Pre-Mitigation Risk H: Pre-Mitigation Risk; Post Mitigation Risk Total: 68 |  |  |  |  | 10
#REF!
11
12
[9 empty] | WTG |  | WTG
[9 empty] | Pre-Mitigation Risk | 14 | Post Mitigation Risk | 7 | 13
14
15
16
17
18
[9 empty] | Other 1 |  | Other 1
[9 empty] | Pre-Mitigation Risk | 10 | Post Mitigation Risk | 11 | 19
Designer Interface Notes
1
2
3
Total
4
| Pre-Mitigation Risk H: Post Mitigation Risk; Post Mitigation Risk Total: 49 | Other 2 |  | Other 2
[9 empty] | Pre-Mitigation Risk | 10 | Post Mitigation Risk | 10 | 5
6
7
8
9
10
[9 empty] | Other 3 |  | Other 3
[9 empty] | Pre-Mitigation Risk | 14 | Post Mitigation Risk | 7 | 11
12
13
14
15

## Civil
Designer |  | Scope | [5 empty] | Project |  | [Insert Project Name Here]
[Insert name / logo here] |  | [Briefly describe project scope here]
|  | Designer | [Insert designer name] |  | Date | [Date completed] |  | Lead Designer | [Insert name of lead designer who is approving DRA] |  | Date | [Date approved] |  | Contact | [insert phone no.] |  | [Insert email address]
| Hazard / Design Area | Risk Type | Phase of Life Cycle at Risk | Pre-mitigation Risk |  |  | Design mitigation required |  | Principal applied & mitigation measures taken by Designer. |  | Post Mitigation Risk Rating | [5 empty] | Information for builders and users.
| Particular / Significant SHE Risks identified |  |  | Likelihood 1-5 | Severity 1-5 | Risk Rating (LxS) |  | Design Assumptions / Constraints | Prevention Principle Applied. | Description of Risk Mitigation by designer. | Residual Likelihood 1-5 | Residual Severity 1-5 | Residual Risk LxS | Included in PH&SP / PCI | Signed off by Lead Designer | Reviewed by PSDP / CDMC | Contractor(s) | Client
[17 empty] | Construction, Fabrication & Installation | Operation, Maintenance & Demolition
A | Off Site Works
A-1 |  |  |  | 5 | 2 | H |  |  |  |  | 2 | 3 | M | [5 empty] | Principles of Prevention
A-2 |  |  |  | 1 | 5 | M |  |  |  |  | 1 | 3 | L | [5 empty] | (a) avoiding risks;
A-3 |  |  |  | 1 | 1 | L |  |  |  |  | 1 | 1 | L | [5 empty] | (b) evaluating the risks which cannot be avoided;
A-4 | [18 empty] | (c) combating the risks at source;
A-5 | [18 empty] | (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined work-rate and to reducing their effect on health.
A-6 | [18 empty] | (e) adapting to technical progress.
A-7 | [18 empty] | (f) replacing the dangerous by the non-dangerous or the less dangerous;
A-8 | [18 empty] | (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment;
A-9 | [10 empty] | 5 | [7 empty] | (h) giving collective protective measures priority over individual protective measures (e.g design in a netting fall arrest system to replace PPE)
A-10 |  |  |  | 1 | 2 | L |  |  |  |  | 1 | 2 | L | [5 empty] | (i) giving appropriate instructions to employees (Information will accompany the design to allow RAMS be prepared)
B | Site Roads & Tracks
B-1 |  |  |  | 1 | 2 | L |  |  |  |  | 1 | 2 | L | [5 empty] | 1
B-2 |  |  |  | 4 | 2 | M |  |  |  |  | 4 | 1 | L | [5 empty] | 2
B-3 | [18 empty] | 3
B-4 | [18 empty] | 4
B-5 | [18 empty] | 5
B-6
B-7
B-8
B-9
B-10
C | WTG Foundations
C-1 | [18 empty] | Phase to which hazard applies
C-2 | [18 empty] | Site Enabling | Site Investigation / Survey
C-3 | [18 empty] | Construction | Construction
C-4 | [18 empty] | Comm. & Test | Commissioning / Testing
C-5 | [18 empty] | Maintenance | Maintenance
C-6 | [18 empty] | Operations | Operations
C-7 | [18 empty] | Decom. | Demolition/Decommissioning/Dismantling
C-8 | [18 empty] | All | All phases of life cycle
C-9
C-10
D | WTG Bases
D-1 | [18 empty] | Yes
D-2 | [18 empty] | No
D-3 | [18 empty] | NA
D-4
D-5 | [18 empty] | Safety
D-6 | [18 empty] | Health
D-7 | [18 empty] | Environment
D-8 | [18 empty] | Other
D-9
D-10
E | Trenching
E-1
E-2
E-3
E-4
E-5
E-6
E-7
E-8
E-9
E-10
F | Transformer Bases
F-1
F-2
F-3
F-4
F-5
F-6
F-7
F-8
F-9
F-10
G | Drainage
G-1
G-2
G-3
G-4
G-5
G-6
G-7
G-8
G-9
G-10
H | Borrow Pits
H-1
H-2
H-3
H-4
H-5
H-6
H-7
H-8
H-9
H-10
I | Material Repositories
I-1
I-2
I-3
I-4
I-5
I-6
I-7
I-8
I-9
I-10
J | Public Safety
J-1
J-2
J-3
J-4
J-5
K | Other 2
K-1
K-2
K-3
K-4
K-5
L | Other 3
L-1
L-2
L-3
L-4
L-5
M | Other 4
M-1
N | Other 5
M-1
o | Other 6
M-1
Note on C4: Safety, Health, Environmental, Other
Note on D4: SI = Site Investigation Cons. = Construction C&T = Commissioning & Testing Op. = Operation Main. = Maintenance Demo. = Demolition All = All phases of life cycle
Note on J5: Henrik Carstens (HEC): The principles of prevention Dutyholders should use these principles to direct their approach to identifying and implementing precautions which are necessary to control risks associated with a project. The general principles of prevention (a) avoiding risks; (b) evaluating the risks which cannot be avoided; (c) combating the risks at source; (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined work-rate and to reducing their effect on health; (e) adapting to technical progress; (f) replacing the dangerous by the non-dangerous or the less dangerous; (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment; (h) giving collective protective measures priority over individual protective measures; and (i) giving appropriate instructions to employees.

## Electrical
Designer |  | Scope | [5 empty] | Project |  | [Insert Project Name Here]
[Insert name / logo here] |  | [Briefly describe project scope here]
|  | Designer | [Insert designer name] |  | Date | [Date completed] |  | Lead Designer | [Insert name of lead designer who is approving DRA] |  | Date | [Date approved] |  | Contact | [insert phone no.] |  | [Insert email address]
| Hazard / Design Area | Risk Type | Phase of Structure Life Cycle at Risk | Pre-mitigation Risk |  |  | Design mitigation required |  | Principal applied & mitigation measures taken by Designer. |  | Post Mitigation Risk Rating | [5 empty] | Information for builders and users.
| Particular / Significant SHE Risks identified |  |  | Likelihood 1-5 | Severity 1-5 | Risk Rating (LxS) |  | Design Assumptions / Constraints | Prevention Principle Applied. | Description of Risk Mitigation by designer. | Residual Likelihood 1-5 | Residual Severity 1-5 | Residual Risk LxS | Included in PH&SP / PCI | Signed off by Lead Designer | Reviewed by PSDP / CDMC | Contractor(s) | Client
[17 empty] | Construction, Fabrication & Installation | Operation, Maintenance & Demolition
A | Electricity
A-1 | Electric shock |  |  | 5 | 2 | H |  |  |  |  | 4 | 2 | M | [5 empty] | Principles of Prevention
A-2 | Burns |  |  | 1 | 5 | M |  |  |  |  | 1 | 3 | L | [5 empty] | (a) avoiding risks;
A-3 | Explosion |  |  | 1 | 1 | L |  |  |  |  | 1 | 1 | L | [5 empty] | (b) evaluating the risks which cannot be avoided;
A-4 | [18 empty] | (c) combating the risks at source;
A-5 | [18 empty] | (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined
A-6 | [18 empty] | (e) adapting to technical progress.
A-7 | [18 empty] | (f) replacing the dangerous by the non-dangerous or the less dangerous;
A-8 | [18 empty] | (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment;
A-9 | [10 empty] | 5 | [7 empty] | (h) giving collective protective measures priority over individual protective measures (e.g design in a netting fall arrest system to replace PPE)
A-10 |  |  |  | 1 | 2 | L |  |  |  |  | 1 | 2 | L | [5 empty] | (i) giving appropriate instructions to employees (Information will accompany the design to allow RAMS be prepared)
B | Height
B-1 | Fall from height |  |  | 1 | 2 | L |  |  |  |  | 1 | 2 | L | [5 empty] | 1
B-2 | Falling objects |  |  | 4 | 2 | M |  |  |  |  | 4 | 1 | L | [5 empty] | 2
B-3 | [18 empty] | 3
B-4 | [18 empty] | 4
B-5 | [18 empty] | 5
B-6
B-7
B-8
B-9
B-10
C | Stored Energy
C-1 | Compressed gasses | [17 empty] | Phase to which hazard applies
C-2 | Charged springs | [17 empty] | SI | Site Investigation / Survey
C-3 | [18 empty] | Cons. | Construction
C-4 | [18 empty] | C/T | Commissioning / Testing
C-5 | [18 empty] | Main. | Maintenance
C-6 | [18 empty] | Op. | Operations
C-7 | [18 empty] | Decom. | Demolition/Decommissioning/Dismantling
C-8 | [18 empty] | All | All phases of life cycle
C-9
C-10
D | Rotating Parts
D-1 | Driveshafts | [17 empty] | Yes
D-2 | Charging motors | [17 empty] | No
D-3 | Switcggear. | [17 empty] | NA
D-4
D-5 | [18 empty] | Safety
D-6 | [18 empty] | Health
D-7 | [18 empty] | Environment
D-8 | [18 empty] | Other
D-9
D-10
E | Moving Parts
E-1 | Drive shafts
E-2 | Switchgear
E-3 | Doors
E-4
E-5
E-6
E-7
E-8
E-9
E-10
F | Hazardous Substances
F-1 | Chemical | Safety
F-2 | Solvents | Safety
F-3 | Oils & greases | Health
F-4 | Gasses (SF6) | Health
F-5 | Oils & greases | Environment
F-6 | Gasses (SF6) | Environment
F-7
F-8
F-9
F-10
G | Public Safety
G-1 | Electric shock
G-2 | Security
G-3
G-4
G-5
G-6
G-7
G-8
G-9
G-10
H | Slips, Trips & Falls
H-1 | Surfaces
H-2 | Gradients
H-3 | Lighting
H-4 | Steps
H-5
H-6
H-7
H-8
H-9
H-10
I | Waste Management
I-1 | Toilets | Environment
I-2
I-3
I-4
I-5
I-6
I-7
I-8
I-9
I-10
J | Other 3
J-1
J-2
J-3
J-4
J-5
K | Other 4
K-1
K-2
K-3
K-4
K-5
L | Other 5
L-1
L-2
L-3
L-4
L-5
M | Other 6
M-1
N | Other 7
M-1
o | Other 8
M-1
Note on C4: Safety, Health, Environmental, Other
Note on D4: SI = Site Investigation Cons. = Construction C&T = Commissioning & Testing Op. = Operation Main. = Maintenance Demo. = Demolition All = All phases of life cycle
Note on J5: Henrik Carstens (HEC): The principles of prevention Dutyholders should use these principles to direct their approach to identifying and implementing precautions which are necessary to control risks associated with a project. The general principles of prevention (a) avoiding risks; (b) evaluating the risks which cannot be avoided; (c) combating the risks at source; (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined work-rate and to reducing their effect on health; (e) adapting to technical progress; (f) replacing the dangerous by the non-dangerous or the less dangerous; (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment; (h) giving collective protective measures priority over individual protective measures; and (i) giving appropriate instructions to employees.

## Wind Turbine
Designer |  | Scope | [5 empty] | Project |  | [Insert Project Name Here]
[Insert name / logo here] |  | [Briefly describe project scope here]
|  | Designer | [Insert designer name] |  | Date | [Date completed] |  | Lead Designer | [Insert name of lead designer who is approving DRA] |  | Date | [Date approved] |  | Contact | [insert phone no.] |  | [Insert email address]
| Hazard / Design Area | Risk Type | Phase of Life Cycle at Greatest Risk | Pre-mitigation Risk |  |  | Design mitigation required |  | Principal applied & mitigation measures taken by Designer. |  | Post Mitigation Risk Rating | [5 empty] | Information for builders and users.
| Particular / Significant SHE Risks identified |  |  | Likelihood 1-5 | Severity 1-5 | Risk Rating (LxS) |  | Design Assumptions / Constraints | Prevention Principle Applied. | Description of Risk Mitigation by designer. | Residual Likelihood 1-5 | Residual Severity 1-5 | Residual Risk LxS | Included in PH&SP / PCI | Signed off by Lead Designer | Reviewed by PSDP / CDMC | Contractor(s) | Client
[17 empty] | Construction, Fabrication & Installation | Operation, Maintenance & Demolition
A | Height
A-1 |  |  |  | 5 | 2 | H |  |  |  |  | 4 | 2 | M | [5 empty] | Principles of Prevention
A-2 |  |  |  | 1 | 5 | M |  |  |  |  | 1 | 3 | L | [5 empty] | (a) avoiding risks;
A-3 |  |  |  | 1 | 1 | L |  |  |  |  | 1 | 1 | L | [5 empty] | (b) evaluating the risks which cannot be avoided;
A-4 | [18 empty] | (c) combating the risks at source;
A-5 | [18 empty] | (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined
A-6 | [18 empty] | (e) adapting to technical progress.
A-7 | [18 empty] | (f) replacing the dangerous by the non-dangerous or the less dangerous;
A-8 | [18 empty] | (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment;
A-9 | [10 empty] | 5 | [7 empty] | (h) giving collective protective measures priority over individual protective measures (e.g design in a netting fall arrest system to replace PPE)
A-10 | [10 empty] | 1 | 2 | L | [5 empty] | (i) giving appropriate instructions to employees (Information will accompany the design to allow RAMS be prepared)
B | Electricity
B-1 |  |  |  | 5 | 2 | H |  |  |  |  | 1 | 2 | L | [5 empty] | 1
B-2 |  |  |  | 5 | 2 | H |  |  |  |  | 4 | 1 | L | [5 empty] | 2
B-3 |  |  |  | 4 | 2 | M | [12 empty] | 3
B-4 | [18 empty] | 4
B-5 | [18 empty] | 5
B-6
B-7
B-8
B-9
B-10
C | Rotating Parts
C-1 | [18 empty] | Phase to which hazard applies
C-2 | [18 empty] | SI | Site Investigation / Survey
C-3 | [18 empty] | Cons. | Construction
C-4 | [18 empty] | Com &Test | Commissioning / Testing
C-5 | [18 empty] | Main. | Maintenance
C-6 | [18 empty] | Op. | Operations
C-7 | [18 empty] | Decom. | Demolition/Decommissioning/Dismantling
C-8 | [18 empty] | All | All phases of life cycle
C-9
C-10
D | Moving Parts
D-1 | [18 empty] | Yes
D-2 | [18 empty] | No
D-3 | [18 empty] | NA
D-4
D-5 | [18 empty] | Safety
D-6 | [18 empty] | Health
D-7 | [18 empty] | Environment
D-8 | [18 empty] | Other
D-9
D-10
E | Noise / Vibration
E-1
E-2
E-3
E-4
E-5
E-6
E-7
E-8
E-9
E-10
F | Hazardous Substances
F-1
F-2
F-3
F-4
F-5
F-6
F-7
F-8
F-9
F-10
G | Heavy Lifting
G-1
G-2
G-3
G-4
G-5
G-6
G-7
G-8
G-9
G-10
H | Restircted Working
H-1
H-2
H-3
H-4
H-5
H-6
H-7
H-8
H-9
H-10
I | Public Safety
I-1
I-2
I-3
I-4
I-5
I-6
I-7
I-8
I-9
I-10
J | Emergency Response
J-1 |  | Environment
J-2
J-3
J-4
J-5
K | Other 2
K-1 |  | Environment
K-2
K-3
K-4
K-5
L | Other 3
L-1 |  | Environment
L-2
L-3
L-4
L-5
M | Other 4
M-1
N | Other 5
M-1
o | Other 6
M-1
Note on C4: Safety, Health, Environmental, Other
Note on D4: SI = Site Investigation Cons. = Construction C&T = Commissioning & Testing Op. = Operation Main. = Maintenance Demo. = Demolition All = All phases of life cycle
Note on J5: Henrik Carstens (HEC): The principles of prevention Dutyholders should use these principles to direct their approach to identifying and implementing precautions which are necessary to control risks associated with a project. The general principles of prevention (a) avoiding risks; (b) evaluating the risks which cannot be avoided; (c) combating the risks at source; (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined work-rate and to reducing their effect on health; (e) adapting to technical progress; (f) replacing the dangerous by the non-dangerous or the less dangerous; (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment; (h) giving collective protective measures priority over individual protective measures; and (i) giving appropriate instructions to employees.

## Other 1
Designer |  | Scope | [5 empty] | Project |  | [Insert Project Name Here]
[Insert name / logo here] |  | [Briefly describe project scope here]
|  | Designer | [Insert designer name] |  | Date | [Date completed] |  | Lead Designer | [Insert name of lead designer who is approving DRA] |  | Date | [Date approved] |  | Contact | [insert phone no.] |  | [Insert email address]
| Hazard / Design Area | Risk Type | Phase of Structure Life Cycle at Risk | Pre-mitigation Risk |  |  | Design mitigation required |  | Principal applied & mitigation measures taken by Designer. |  | Post Mitigation Risk Rating | [5 empty] | Information for builders and users.
| Particular / Significant SHE Risks identified |  |  | Likelihood 1-5 | Severity 1-5 | Risk Rating (LxS) |  | Design Assumptions / Constraints | Prevention Principle Applied. | Description of Risk Mitigation by designer. | Residual Likelihood 1-5 | Residual Severity 1-5 | Residual Risk LxS | Included in PH&SP / PCI | Signed off by Lead Designer | Reviewed by PSDP / CDMC | Contractor(s) | Client
[17 empty] | Construction, Fabrication & Installation | Operation, Maintenance & Demolition
A
A-1 |  |  |  | 5 | 2 | H | Yes |  |  |  | 5 | 2 | H | [5 empty] | Principles of Prevention
A-2 |  |  |  | 1 | 5 | M |  |  |  |  | 1 | 3 | L | [5 empty] | (a) avoiding risks;
A-3 |  |  |  | 1 | 1 | L |  |  |  |  | 1 | 1 | L | [5 empty] | (b) evaluating the risks which cannot be avoided;
A-4 | [18 empty] | (c) combating the risks at source;
A-5 | [18 empty] | (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined
A-6 | [18 empty] | (e) adapting to technical progress.
A-7 | [18 empty] | (f) replacing the dangerous by the non-dangerous or the less dangerous;
A-8 | [18 empty] | (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment;
A-9 | [18 empty] | (h) giving collective protective measures priority over individual protective measures (e.g design in a netting fall arrest system to replace PPE)
A-10 |  |  |  | 1 | 2 | L | [12 empty] | (i) giving appropriate instructions to employees (Information will accompany the design to allow RAMS be prepared)
B
B-1 |  |  |  | 1 | 2 | L |  |  |  |  | 5 | 2 | H | [5 empty] | 1
B-2 |  |  |  | 4 | 2 | M |  |  |  |  | 5 | 1 | M | [5 empty] | 2
B-3 | [10 empty] | 4 | 1 | L | [5 empty] | 3
B-4 | [18 empty] | 4
B-5 | [18 empty] | 5
B-6
B-7
B-8
B-9
B-10
C
C-1 | [18 empty] | Phase to which hazard applies
C-2 | [18 empty] | SI | Site Investigation / Survey
C-3 | [18 empty] | Cons. | Construction
C-4 | [18 empty] | C/T | Commissioning / Testing
C-5 | [18 empty] | Main. | Maintenance
C-6 | [18 empty] | Op. | Operations
C-7 | [18 empty] | Decom. | Demolition/Decommissioning/Dismantling
C-8 | [18 empty] | All | All phases of life cycle
C-9
C-10
D
D-1 | [18 empty] | Yes
D-2 | [18 empty] | No
D-3 | [18 empty] | NA
D-4
D-5 | [18 empty] | Safety
D-6 | [18 empty] | Health
D-7 | [18 empty] | Environment
D-8 | [18 empty] | Other
D-9
D-10
E
E-1
E-2
E-3
E-4
E-5
E-6
E-7
E-8
E-9
E-10
F
F-1
F-2
F-3
F-4
F-5
F-6
F-7
F-8
F-9
F-10
G
G-1
G-2
G-3
G-4
G-5
G-6
G-7
G-8
G-9
G-10
H
H-1
H-2
H-3
H-4
H-5
H-6
H-7
H-8
H-9
H-10
I
I-1
I-2
I-3
I-4
I-5
I-6
I-7
I-8
I-9
I-10
J
J-1
J-2
J-3
J-4
J-5
K
K-1
K-2
K-3
K-4
K-5
L
L-1
L-2
L-3
L-4
L-5
M
M-1
N
M-1
o
M-1
Note on C4: Safety, Health, Environmental, Other
Note on D4: SI = Site Investigation Cons. = Construction C&T = Commissioning & Testing Op. = Operation Main. = Maintenance Demo. = Demolition All = All phases of life cycle
Note on J5: Henrik Carstens (HEC): The principles of prevention Dutyholders should use these principles to direct their approach to identifying and implementing precautions which are necessary to control risks associated with a project. The general principles of prevention (a) avoiding risks; (b) evaluating the risks which cannot be avoided; (c) combating the risks at source; (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined work-rate and to reducing their effect on health; (e) adapting to technical progress; (f) replacing the dangerous by the non-dangerous or the less dangerous; (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment; (h) giving collective protective measures priority over individual protective measures; and (i) giving appropriate instructions to employees.

## Other 2
Designer |  | Scope | [5 empty] | Project |  | [Insert Project Name Here]
[Insert name / logo here] |  | [Briefly describe project scope here]
|  | Designer | [Insert designer name] |  | Date | [Date completed] |  | Lead Designer | [Insert name of lead designer who is approving DRA] |  | Date | [Date approved] |  | Contact | [insert phone no.] |  | [Insert email address]
| Hazard / Design Area | Risk Type | Phase of Structure Life Cycle at Risk | Pre-mitigation Risk |  |  | Design mitigation required |  | Principal applied & mitigation measures taken by Designer. |  | Post Mitigation Risk Rating | [5 empty] | Information for builders and users.
| Particular / Significant SHE Risks identified |  |  | Likelihood 1-5 | Severity 1-5 | Risk Rating (LxS) |  | Design Assumptions / Constraints | Prevention Principle Applied. | Description of Risk Mitigation by designer. | Residual Likelihood 1-5 | Residual Severity 1-5 | Residual Risk LxS | Included in PH&SP / PCI | Signed off by Lead Designer | Reviewed by PSDP / CDMC | Contractor(s) | Client
[17 empty] | Construction, Fabrication & Installation | Operation, Maintenance & Demolition
A
A-1 |  |  |  | 5 | 2 | H | Yes |  |  |  | 4 | 2 | M | [5 empty] | Principles of Prevention
A-2 |  |  |  | 1 | 5 | M |  |  |  |  | 1 | 3 | L | [5 empty] | (a) avoiding risks;
A-3 |  |  |  | 1 | 1 | L |  |  |  |  | 1 | 1 | L | [5 empty] | (b) evaluating the risks which cannot be avoided;
A-4 | [18 empty] | (c) combating the risks at source;
A-5 | [18 empty] | (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined
A-6 | [18 empty] | (e) adapting to technical progress.
A-7 | [18 empty] | (f) replacing the dangerous by the non-dangerous or the less dangerous;
A-8 | [18 empty] | (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment;
A-9 | [18 empty] | (h) giving collective protective measures priority over individual protective measures (e.g design in a netting fall arrest system to replace PPE)
A-10 |  |  |  | 1 | 2 | L | [12 empty] | (i) giving appropriate instructions to employees (Information will accompany the design to allow RAMS be prepared)
B
B-1 |  |  |  | 1 | 2 | L |  |  |  |  | 5 | 2 | H | [5 empty] | 1
B-2 |  |  |  | 4 | 2 | M |  |  |  |  | 5 | 1 | M | [5 empty] | 2
B-3 | [10 empty] | 4 | 1 | L | [5 empty] | 3
B-4 | [18 empty] | 4
B-5 | [18 empty] | 5
B-6
B-7
B-8
B-9
B-10
C
C-1 | [18 empty] | Phase to which hazard applies
C-2 | [18 empty] | SI | Site Investigation / Survey
C-3 | [18 empty] | Cons. | Construction
C-4 | [18 empty] | C/T | Commissioning / Testing
C-5 | [18 empty] | Main. | Maintenance
C-6 | [18 empty] | Op. | Operations
C-7 | [18 empty] | Decom. | Demolition/Decommissioning/Dismantling
C-8 | [18 empty] | All | All phases of life cycle
C-9
C-10
D
D-1 | [18 empty] | Yes
D-2 | [18 empty] | No
D-3 | [18 empty] | NA
D-4
D-5 | [18 empty] | Safety
D-6 | [18 empty] | Health
D-7 | [18 empty] | Environment
D-8 | [18 empty] | Other
D-9
D-10
E
E-1
E-2
E-3
E-4
E-5
E-6
E-7
E-8
E-9
E-10
F
F-1
F-2
F-3
F-4
F-5
F-6
F-7
F-8
F-9
F-10
G
G-1
G-2
G-3
G-4
G-5
G-6
G-7
G-8
G-9
G-10
H
H-1
H-2
H-3
H-4
H-5
H-6
H-7
H-8
H-9
H-10
I
I-1
I-2
I-3
I-4
I-5
I-6
I-7
I-8
I-9
I-10
J
J-1
J-2
J-3
J-4
J-5
K
K-1
K-2
K-3
K-4
K-5
L
L-1
L-2
L-3
L-4
L-5
M
M-1
N
M-1
o
M-1
Note on C4: Safety, Health, Environmental, Other
Note on D4: SI = Site Investigation Cons. = Construction C&T = Commissioning & Testing Op. = Operation Main. = Maintenance Demo. = Demolition All = All phases of life cycle
Note on J5: Henrik Carstens (HEC): The principles of prevention Dutyholders should use these principles to direct their approach to identifying and implementing precautions which are necessary to control risks associated with a project. The general principles of prevention (a) avoiding risks; (b) evaluating the risks which cannot be avoided; (c) combating the risks at source; (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined work-rate and to reducing their effect on health; (e) adapting to technical progress; (f) replacing the dangerous by the non-dangerous or the less dangerous; (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment; (h) giving collective protective measures priority over individual protective measures; and (i) giving appropriate instructions to employees.

## Other 3
Designer |  | Scope | [5 empty] | Project |  | [Insert Project Name Here]
[Insert name / logo here] |  | [Briefly describe project scope here]
|  | Designer | [Insert designer name] |  | Date | [Date completed] |  | Lead Designer | [Insert name of lead designer who is approving DRA] |  | Date | [Date approved] |  | Contact | [insert phone no.] |  | [Insert email address]
| Hazard / Design Area | Risk Type | Phase of Structure Life Cycle at Risk | Pre-mitigation Risk |  |  | Design mitigation required |  | Principal applied & mitigation measures taken by Designer. |  | Post Mitigation Risk Rating | [5 empty] | Information for builders and users.
| Particular / Significant SHE Risks identified |  |  | Likelihood 1-5 | Severity 1-5 | Risk Rating (LxS) |  | Design Assumptions / Constraints | Prevention Principle Applied. | Description of Risk Mitigation by designer. | Residual Likelihood 1-5 | Residual Severity 1-5 | Residual Risk LxS | Included in PH&SP / PCI | Signed off by Lead Designer | Reviewed by PSDP / CDMC | Contractor(s) | Client
[17 empty] | Construction, Fabrication & Installation | Operation, Maintenance & Demolition
A
A-1 |  |  |  | 5 | 2 | H | Yes |  |  |  | 4 | 2 | M | [5 empty] | Principles of Prevention
A-2 |  |  |  | 1 | 5 | M |  |  |  |  | 1 | 3 | L | [5 empty] | (a) avoiding risks;
A-3 |  |  |  | 1 | 1 | L |  |  |  |  | 1 | 1 | L | [5 empty] | (b) evaluating the risks which cannot be avoided;
A-4 | [18 empty] | (c) combating the risks at source;
A-5 | [18 empty] | (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined
A-6 | [18 empty] | (e) adapting to technical progress.
A-7 | [18 empty] | (f) replacing the dangerous by the non-dangerous or the less dangerous;
A-8 | [18 empty] | (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment;
A-9 | [10 empty] | 5 | [7 empty] | (h) giving collective protective measures priority over individual protective measures (e.g design in a netting fall arrest system to replace PPE)
A-10 | [10 empty] | 1 | 2 | L | [5 empty] | (i) giving appropriate instructions to employees (Information will accompany the design to allow RAMS be prepared)
B
B-1 |  |  |  | 5 | 2 | H |  |  |  |  | 1 | 2 | L | [5 empty] | 1
B-2 |  |  |  | 5 | 2 | H |  |  |  |  | 4 | 1 | L | [5 empty] | 2
B-3 |  |  |  | 4 | 2 | M | [12 empty] | 3
B-4 | [18 empty] | 4
B-5 | [18 empty] | 5
B-6
B-7
B-8
B-9
B-10
C
C-1 | [18 empty] | Phase to which hazard applies
C-2 | [18 empty] | SI | Site Investigation / Survey
C-3 | [18 empty] | Cons. | Construction
C-4 | [18 empty] | C/T | Commissioning / Testing
C-5 | [18 empty] | Main. | Maintenance
C-6 | [18 empty] | Op. | Operations
C-7 | [18 empty] | Decom. | Demolition/Decommissioning/Dismantling
C-8 | [18 empty] | All | All phases of life cycle
C-9
C-10
D
D-1 | [18 empty] | Yes
D-2 | [18 empty] | No
D-3 | [18 empty] | NA
D-4
D-5 | [18 empty] | Safety
D-6 | [18 empty] | Health
D-7 | [18 empty] | Environment
D-8 | [18 empty] | Other
D-9
D-10
E
E-1
E-2
E-3
E-4
E-5
E-6
E-7
E-8
E-9
E-10
F
F-1
F-2
F-3
F-4
F-5
F-6
F-7
F-8
F-9
F-10
G
G-1
G-2
G-3
G-4
G-5
G-6
G-7
G-8
G-9
G-10
H
H-1
H-2
H-3
H-4
H-5
H-6
H-7
H-8
H-9
H-10
I
I-1
I-2
I-3
I-4
I-5
I-6
I-7
I-8
I-9
I-10
J
J-1
J-2
J-3
J-4
J-5
K
K-1
K-2
K-3
K-4
K-5
L
L-1
L-2
L-3
L-4
L-5
M
M-1
N
M-1
o
M-1
Note on C4: Safety, Health, Environmental, Other
Note on D4: SI = Site Investigation Cons. = Construction C&T = Commissioning & Testing Op. = Operation Main. = Maintenance Demo. = Demolition All = All phases of life cycle
Note on J5: Henrik Carstens (HEC): The principles of prevention Dutyholders should use these principles to direct their approach to identifying and implementing precautions which are necessary to control risks associated with a project. The general principles of prevention (a) avoiding risks; (b) evaluating the risks which cannot be avoided; (c) combating the risks at source; (d) adapting the work to the individual, especially as regards the design of workplaces, the choice of work equipment and the choice of working and production methods, with a view, in particular, to alleviating monotonous work and work at a predetermined work-rate and to reducing their effect on health; (e) adapting to technical progress; (f) replacing the dangerous by the non-dangerous or the less dangerous; (g) developing a coherent overall prevention policy which covers technology, organisation of work, working conditions, social relationships and the influence of factors relating to the working environment; (h) giving collective protective measures priority over individual protective measures; and (i) giving appropriate instructions to employees.